## Gantt_Chart
BRIGHT TV VIEWERSHIP — Project Plan & Gantt Chart
Project start: 03 Aug 2026 ¦ Bright Tv Viewership Portfolio project
Task | Phase | Owner | Start Date | End Date | Duration (days) | % Complete | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26
Project Scoping & Objective Definition | 1. Initiation | Alice | 2026-08-03 | 2026-08-04 | 2 | 100%
Data Collection & Understanding | 2. Data Prep | Alice | 2026-08-05 | 2026-08-07 | 3 | 100%
Data Cleaning (SQL) — duration parsing, nulls | 2. Data Prep | Alice | 2026-08-07 | 2026-08-10 | 4 | 100%
Exploratory Data Analysis | 3. Analysis | Alice | 2026-08-10 | 2026-08-13 | 4 | 100%
Pivot Tables & Dashboard Build (Excel) | 3. Analysis | Alice | 2026-08-12 | 2026-08-16 | 5 | 100%
Insights & Presentation Deck (PowerPoint) | 4. Communicate | Alice | 2026-08-17 | 2026-08-20 | 4 | 100%
Project Planning Board (Miro) | 1. Initiation | Alice | 2026-08-03 | 2026-08-08 | 6 | 40%
GitHub Repository & Documentation | 5. Publish | Alice | 2026-08-20 | 2026-08-23 | 4 | 20%
Final Review & Submission | 5. Publish | Alice | 2026-08-23 | 2026-08-24 | 2 | 0%
Phase Legend
1. Initiation
2. Data Prep
3. Analysis
4. Communicate
5. Publish